## OVERVIEW
ReconX — Advanced Track ticket tracker
Day | Tickets | Done this cohort | Already satisfied | Needs attention | Notes recorded
DAY 1 | 17 | 1 | 14 | 2 | 1
DAY 2 | 15 | 11 | 4 | 0 | 0
DAY 3 | 15 | 10 | 0 | 2 | 1
DAY 4 | 15 | 10 | 4 | 1 | 2
DAY 5 | 18 | 16 | 1 | 1 | 6
DAY 6 | 17 | 15 | 2 | 0 | 11
DAY 7 | 13 | 9 | 0 | 4 | 2
DAY 8 | 17 | 14 | 0 | 1 | 9
DAY 9 | 18 | 16 | 2 | 0 | 16
DAY 10 | 20 | 3 | 7 | 4 | 4
TOTAL | 165 | 105 | 34 | 15 | 52
Status colour key
DONE — worked on and completed as this ticket
Already DONE — the requirement was already satisfied when the ticket was reached, because an earlier ticket's work already covered it (or it came with the scaffold). Not a separate delivery.
Needs a decision or follow-up (CHECK, PR, JAVADOC, Don't do?)
Broken, missing, or not started (ERROR, Missing, NOT EXIST, NOT DONE YET)
No status recorded

## DAY_1
DAY 1 · 17 tickets · ADV001 – ADV017
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV001 | Already DONE |  | Create GitHub repo with branch protection | Stand up a private team repository with enforced branch protection rules on `main` and `develop`, plus a CODEOWNERS file that routes PR reviews to the right team lead. What: A private team repo with branch protection on `main` (2 approvals + Code Owners + status checks) and `develop` (1 approval), plus `.github/CODEOWNERS` routing reviews by path. | Team note (original tracker): Create repo
TICKET-ADV002 | DONE | NA | Design C4 Context diagram | Produce a C4 Level 1 (Context) diagram for ReconX showing the system as a single box, the human actors who interact with it, and the external systems it talks to. What: `db/diagrams/c4-context.md` containing a single `C4Context` Mermaid block with four personas, one ReconX system box, and six external systems (OMS, SFTP, Bloomberg, email, SSO, Grafana).
TICKET-ADV003 | Already DONE |  | Design C4 Container diagram | Produce a C4 Level 2 (Container) diagram showing each independently deployable unit inside the ReconX boundary, and how they communicate. What: `db/diagrams/c4-container.md` showing the seven runtime containers (React SPA, API, recon engine, Postgres, Kafka, Prometheus, Grafana) inside a `System_Boundary(reconxBoundary)` block.
TICKET-ADV004 | Already DONE |  | Design C4 Component diagram | Produce a C4 Level 3 (Component) diagram for ONE container — usually the recon-service API — showing its major logical components and how they wire together. What: `db/diagrams/c4-component.md` zooming into ONE container (the recon-service API) and showing its components: REST controllers, security filter, services, Kafka producer/consumer, repositories.
TICKET-ADV005 | Missing |  | — ticket does not exist — | No such ticket exists in the Day 1 guide — numbering gap.
TICKET-ADV006 | Already DONE |  | Design ER model (8 entities) | Produce an entity-relationship diagram covering the eight core ReconX tables with primary keys, foreign keys, and key columns annotated. What: `db/diagrams/erd.md` with a Mermaid `erDiagram` declaring exactly eight tables (counterparties, instruments, users, trades, settlements, recon_jobs, recon_breaks, audit_log), PK / FK columns marked, FK arrows drawn.
TICKET-ADV007 | Already DONE |  | CREATE TABLE with monthly partitioning | Create the `trades` table as a RANGE-partitioned parent table on `trade_date`, with one child partition per calendar month for the active window plus a DEFAULT partition for safety. What: `trades` parent table created with `PARTITION BY RANGE (trade_date)`, plus child partitions `trades_2026_01` … `trades_2026_04` and a `trades_default` catch-all.
TICKET-ADV008 | CHECK |  | Materialised view: mv_daily_recon_summary | Create a materialised view that aggregates trades and recon breaks by trade_date, region, and asset class, and make it refreshable concurrently without blocking dashboard reads. What: A materialised view aggregating trades + breaks by trade_date / region / asset_class, with a UNIQUE INDEX on those columns so `REFRESH MATERIALIZED VIEW CONCURRENTLY` works.
TICKET-ADV009 | Already DONE |  | Add JSONB column to instruments | Add a `metadata` JSONB column to the `instruments` table for schema-flexible attributes (sector, issuer, rating, tags) and back it with a GIN index optimised for containment queries. What: `instruments.metadata JSONB NOT NULL DEFAULT '{}'::jsonb` column plus `CREATE INDEX ... USING gin (metadata jsonb_path_ops)`.
TICKET-ADV010 | Already DONE |  | Window Function: VWAP per instrument per day | Write a query that returns every trade row alongside its instrument-day volume-weighted average price, using a window function so per-row detail is preserved. What: A SQL query that returns every trade row plus an extra `vwap` column computed via `SUM(price*quantity) OVER (PARTITION BY instrument_id, trade_date) / SUM(quantity) OVER (...)`.
TICKET-ADV011 | Already DONE |  | Recursive CTE: trade lifecycle rollup | Write a recursive CTE that walks each trade through its lifecycle stages (execution → confirmation → settlement → recon break → resolution) and emits one row per stage per trade. What: A recursive CTE with a base case (every trade as `stage='EXECUTION'`) UNION ALL'd with a recursive step that adds CONFIRMATION → SETTLEMENT → RECON_BREAK → RESOLUTION.
TICKET-ADV012 | Already DONE |  | Liquibase master changelog | Wire a Liquibase master changelog that uses `<include>` to compose one-changeset-per-file chapter files, and configure Spring Boot to run the changelog at startup. What: `backend/src/main/resources/db/changelog/db.changelog-master.xml` with the standard Liquibase XSD header and `<include file="changes/XXX-xxx.xml" relativeToChangelogFile="true"/>` lines for each chapter file.
TICKET-ADV013 | Already DONE |  | Add rollback tags | Make every changeset reversible — either via Liquibase's auto-rollback for structured changes or an explicit `<rollback>` block for SQL passthrough — and mark release boundaries with `<tagDatabase>` so the schema can be rolled back to a named point. What: Every non-trivial changeset has a matching `<rollback>` block (or relies on Liquibase auto-rollback for structured changes), and each release boundary is marked with a `<tagDatabase tag="day1-baseline"/>` changeset.
TICKET-ADV014 | Already DONE |  | Add preconditions | Guard each changeset with a `<preConditions>` block that asks "should this run on THIS database right now?" using the appropriate `onFail` mode for the situation. What: Each idempotent schema changeset wraps its content in `<preConditions onFail="MARK_RAN">` (e.g., `<not><tableExists/></not>` for CREATE TABLE) so reapplying the changelog is safe.
TICKET-ADV015 | Already DONE |  | Use Claude to generate ADRs | Author at least three Architecture Decision Records in the Michael Nygard format covering real decisions made today (e.g., partition by trade_date, JSONB for metadata, GIN over btree), using Claude to draft each and committing the prompt alongside the output. What: At least three ADRs under `docs/adr/` in Michael Nygard format (Context / Decision / Status / Consequences) covering today's real choices (partition-by-trade_date, JSONB-for-metadata, GIN-over-btree). The Claude prompt used to draft each is committed alongside.
TICKET-ADV016 | Already DONE |  | Set up Jira / Kanban with epics | Create a project board (Jira or GitHub Projects) with epics that group related work, one card per Day-1 exercise, and a sensible column workflow. What: A project board (Jira or GitHub Projects) with at least three epics grouping the 17 Day-1 exercises, one card per exercise tagged with story points, owner, and acceptance criteria pasted from this guide.
TICKET-ADV017 | Already DONE |  | Seed data: 10 counterparties, 50 instruments, 500 trades | Load deterministic seed data into the database — 10 counterparties, 50 instruments (5 explicit + 45 generated), and 500 trades spread across four monthly partitions — via a Liquibase changeset or `db/seed_data.sql`. What: A Liquibase changeset (or `db/seed_data.sql`) loading 10 counterparties, 50 instruments (5 explicit + 45 generated), and 500 trades spread across the four monthly partitions of `trades`.

## DAY_2
DAY 2 · 15 tickets · ADV018 – ADV032
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV018 | Already DONE |  | Sealed interface `TradeType` and abstract base | Establish the closed-world polymorphic root for every trade type in the platform, plus an internal shared-state base class. What: A `sealed interface TradeType permits EquityTrade, FXTrade, BondTrade, DerivativeTrade` in `com.dbtraining.reconx.model`, plus a package-private abstract base holding `tradeRef`, `notional`, `tradeDate` and validating them non-null in its constructor.
TICKET-ADV019 | DONE | DONE & PASSED | `EquityTrade` with Builder pattern | Implement the first concrete trade with a fluent Builder that enforces required fields and domain invariants at build time. What: `model/EquityTrade.java`: a `final` class with private constructor, static `builder()`, inner `Builder` running `Objects.requireNonNull` and invariant checks inside `build()`, plus a `Side` enum (BUY/SELL) replacing any stringly-typed direction.
TICKET-ADV020 | DONE | PASSED | `FXTrade` (two currencies and FX rate) | Build the FX trade type with two currency fields, a notional in the base currency, and an FX rate — all type-safe. What: `model/FXTrade.java` mirroring the `EquityTrade` shape but with `Currency ccy1`/`ccy2` (never `String`), `BigDecimal notionalCcy1`/`fxRate`, and Builder invariants rejecting equal currencies and non-positive `fxRate`.
TICKET-ADV021 | DONE | PASSED | `BondTrade` (coupon, maturity, face value, ISIN) | Build the bond trade type with fixed-income-specific fields and fail-fast validation on maturity ordering and ISIN shape. What: `model/BondTrade.java` with `BigDecimal couponRate`/`faceValue` (no `double` or `float` anywhere), a Builder that rejects `maturityDate` not strictly after `tradeDate`, and a length-12 ISIN shape check.
TICKET-ADV022 | DONE | PASSED | `DerivativeTrade` (underlying, strike, expiry, option type) | Build the derivative trade type with an option-type enum and strike/expiry validation, without over-validating historical records. What: `model/DerivativeTrade.java` with a nested `enum OptionType { CALL, PUT }`, positive-`BigDecimal` strike, and a Builder check that `expiry` is strictly after `tradeDate` — but NO check against `LocalDate.now()`.
TICKET-ADV023 | DONE | PASSED | `TradeFactory` | Build a single entry point that constructs any concrete `TradeType` from a discriminator string and a parameter map, absorbing the cost of type erasure so callers stay clean. What: `model/TradeFactory.java`: `final` class, `private` constructor, single static `create(String, Map<String, Object>)` dispatching via a Java 25 switch expression over `TradeType.AssetClass` to four private helpers, one per builder from ADV019-ADV022.
TICKET-ADV024 | DONE | PASSED | `Money` and `TradeRef` value objects | Introduce two immutable value objects: `Money` (amount plus currency) and `TradeRef` (regex-validated trade reference). What: Two records in `com.dbtraining.reconx.model`: `Money(BigDecimal amount, Currency currency)` with a compact constructor rejecting negatives plus a `plus(Money)` that throws on currency mismatch, and `TradeRef(String value)` validated against `^[A-Z]{3}-\d{8}-\d{4}$` in its compact constructor.
TICKET-ADV025 | DONE | NONE | Exception hierarchy | Define the platform's exception ladder rooted at an abstract `ReconException`, with four concrete subtypes covering construction, lookup, duplication, and reconciliation outcomes. What: Five files in `com.dbtraining.reconx.exception`: `abstract ReconException extends RuntimeException` with `(String)` and `(String, Throwable)` protected constructors, plus `InvalidTradeException`, `TradeNotFoundException`, `DuplicateTradeRefException`, `ReconciliationMismatchException` each delegating both constructors up.
TICKET-ADV026 | DONE | DONE & PASSED | `ReconciliationRule` enum | Model the closed set of reconciliation tolerance rules as an enum, with thresholds and a behaviour method on each constant. What: `model/ReconciliationRule.java`: an enum with at least four constants carrying `BigDecimal` thresholds via a private constructor, and a `matches(BigDecimal, BigDecimal, BigDecimal, BigDecimal)` method comparing two `(price, quantity)` pairs using `compareTo` only.
TICKET-ADV027 | DONE | NA | `Comparable<TradeType>` natural ordering | Give `TradeType` a natural ordering that is safe for `TreeSet` and `TreeMap` and consistent with the equality you will add in TICKET-ADV028. What: `TradeType` declared `extends Comparable<TradeType>`, with a `static final Comparator<TradeType> NATURAL` built from `comparing(TradeType::tradeDate).reversed().thenComparing(t -> t.tradeRef().value())` and a `default int compareTo(...)` delegating to it.
TICKET-ADV028 | DONE | DONE & PASSED | `equals` and `hashCode` keyed on `tradeRef` | Implement value-based equality on every concrete trade, keyed on the natural business key (`tradeRef`), so collections behave correctly pre- and post-persist. What: An `equals` override on each of `EquityTrade`, `FXTrade`, `BondTrade`, `DerivativeTrade` using `instanceof` pattern matching against the concrete class and comparing `tradeRef`, plus a `hashCode()` returning `tradeRef.hashCode()`.
TICKET-ADV029 | Already DONE |  | JSR-380 validation on the request DTO | Add declarative validation to the inbound HTTP DTO, leaving the domain Builder as the second line of defence. What: `dto/TradeRequest.java`: a record in `com.dbtraining.reconx.dto` with `jakarta.validation.constraints` annotations (`@NotNull`, `@NotBlank`, `@Positive`, `@PositiveOrZero`, `@Pattern`) on every component, one annotation per line.
TICKET-ADV030 | DONE | NA | PII-safe `toString` for logging | Override `toString` on every concrete trade so that default logging never leaks counterparty or settlement PII. What: A hand-written `toString()` override on every concrete trade (`EquityTrade`, `FXTrade`, `BondTrade`, `DerivativeTrade`) including `tradeRef`, instrument identifier, commercial numerics, and `side` — formatted via `String.formatted(...)` with `BigDecimal.toPlainString()` and excluding `counterpartyId`.
TICKET-ADV031 | Already DONE | JAVADOC | Javadoc on all public domain classes | Document the public contract of every domain class and public method so that a reader of the Javadoc could re-implement against it without reading the code. What: Class-level Javadoc in `WHAT / HOW / WHY` style on every public type in `model/` and `exception/`, plus `@param`/`@return`/`@throws` on every public method — including unchecked exceptions like `NullPointerException`/`IllegalStateException` thrown by Builder `build()`.
TICKET-ADV032 | Already DONE | JAVADOC | PR review with two approvals | Open a pull request containing the day's work and obtain two reviewers' approval before merging into the team branch. What: A pushed feature branch (`feature/day2-trade-model`), a PR opened via `gh pr create` against the team integration branch carrying the eleven-item reviewer checklist inline, and two distinct teammate approvals before the merge button is clicked.

## DAY_3
DAY 3 · 15 tickets · ADV033 – ADV047
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV033 | PR |  | ReconciliationEngine using Streams | Build a `reconcile(internal, external)` method on `ReconciliationEngine` that pairs trades from two lists and returns a map of results keyed by trade reference. What: `backend/src/main/java/com/dbtraining/reconx/service/ReconciliationEngine.java` exposes `reconcile(List<Trade> internal, List<Trade> external)` returning a `Map<String, ReconResult>`, built by pre-indexing the external side via `Collectors.toMap` keyed on `tradeRef`.
TICKET-ADV034 | DONE |  | Trade analytics with Collectors | Compute, per counterparty, a one-pass summary of trade notionals (count, sum, min, max, average). What: `service/TradeAnalyticsService.notionalByCounterparty(List<? extends TradeType>)` returns `Map<Long, NotionalSummary>` (or `DoubleSummaryStatistics`) using `Collectors.groupingBy` with a single-pass downstream summariser.
TICKET-ADV035 | DONE |  | VWAP via a custom Collector | Write a custom `Collector<Trade, ?, BigDecimal>` that computes the volume-weighted average price across a stream of trades. What: `service/VwapCollector` (or an inner class on `TradeAnalyticsService`) implements all four `Collector` contributions plus `Characteristics.UNORDERED`, producing `BigDecimal` VWAP to 4 decimal places with `RoundingMode.HALF_UP`.
TICKET-ADV036 | DONE |  | P&L per instrument | Produce a `Map<String, BigDecimal>` of summed P&L per instrument symbol from a list of trades. What: `TradeAnalyticsService.pnlByInstrument(List<EquityTrade>)` returns `Map<String, BigDecimal>` using `groupingBy(EquityTrade::instrumentSymbol, mapping(this::pnl, reducing(BigDecimal.ZERO, BigDecimal::add)))`.
TICKET-ADV037 | DONE |  | CompletableFuture: parallel recon by counterparty | Split the reconciliation by counterparty so that each counterparty is reconciled on its own thread, then merge the results back into a single map. What: `ReconciliationEngine.reconcileByCounterparty(...)` groups both sides by counterparty id, fans out one `CompletableFuture.supplyAsync(..., executor)` per counterparty on an explicit bounded `ExecutorService`, and merges results via `allOf(...).thenApply(...)`.
TICKET-ADV038 | DONE |  | Custom Collector returning a ReconSummary | Write a Collector over a `Stream<ReconResult>` that returns a `ReconSummary` domain object carrying `total`, `matched`, and `broken` counts. What: `service/ReconSummaryCollector implements Collector<ReconResult, ReconSummary.Builder, ReconSummary>` with a mutable inner `Builder`, an accumulator that increments `total` plus one of `matched`/`broken`, and `Characteristics.UNORDERED` only (no `IDENTITY_FINISH`, no `CONCURRENT`).
TICKET-ADV039 | DONE |  | Optional chaining for null-safe lookups | Implement `counterpartyForTradeRef(String tradeRef)` that walks from a trade reference to its counterparty using `Optional` chaining, without any `if (x != null)` or `isPresent()` checks. What: `service/TradeLookupService.counterpartyForTradeRef(String)` is a single expression: `tradeRepo.findByRef(ref).map(Trade::counterpartyId).flatMap(cpRepo::findById).orElseThrow(...)`.
TICKET-ADV040 | DONE |  | Exact-match TDD cycle | Drive an exact-match test through red → green → refactor for the `reconcile` method. What: `backend/src/test/java/com/dbtraining/reconx/service/ReconciliationEngineTest.java` carries `testReconcile_exactMatch_returnsMatched` with `@DisplayName`, given/when/then comment blocks, and AssertJ `assertThat(out).hasSize(1)` then `.status()).isEqualTo(MATCHED)`.
TICKET-ADV041 | DONE |  | Tolerance test with @ParameterizedTest | Drive a parameterised test that runs the same matching assertion over multiple price differences within the tolerance threshold. What: A `@ParameterizedTest(name = "price diff {0} stays within 1% tolerance -> MATCHED")` method on `ReconciliationEngineTest` feeds `@ValueSource(strings = {"0.10", "0.50", "0.99"})` and parses each input via `new BigDecimal(diff)` — no `double` literals anywhere.
TICKET-ADV042 | DONE |  | Missing counterparty trade | Assert that an internal trade with no matching external trade produces a `BREAK` carrying the reason `MISSING_COUNTERPARTY_TRADE`. What: A `testReconcile_missingCounterpartyTrade_returnsBreak` test in `ReconciliationEngineTest` supplies one internal `EquityTrade` plus `List.of()` external and fires two distinct AssertJ assertions — `status()` equals `BREAK` and `discrepancyType()` equals `"MISSING_EXTERNAL"` by exact equality.
TICKET-ADV043 |  |  | Mockito ArgumentCaptor | Use `ArgumentCaptor` to assert that the *content* of the `ReconResult` passed to the repository's `save` method is correct — not just that `save` was called. What: `backend/src/test/java/com/dbtraining/reconx/service/ReconciliationServiceTest.java` uses `mock(ReconResultRepository.class)`, calls `service.runRecon(...)`, then `verify(repo).save(captor.capture())` with `ArgumentCaptor<ReconResult>` and asserts on `captor.getValue().tradeRef()` and `.status()`.
TICKET-ADV044 |  |  | Set up Testcontainers PostgreSQL | Stand up a Testcontainers-managed PostgreSQL container that the Spring Boot test context can talk to. What: A `ReconciliationIntegrationTest` annotated `@SpringBootTest` and `@Testcontainers` declares `static @Container PostgreSQLContainer<?> postgres = new PostgreSQLContainer<>("postgres:16-alpine")` and a `static @DynamicPropertySource` that wires `spring.datasource.url/username/password` from `postgres::getJdbcUrl` and friends.
TICKET-ADV045 | DONE | DONE & PASSED | Integration test: insert → recon → verify | Write an end-to-end test that inserts trades via repository beans, runs the reconciliation service, and verifies the persisted `ReconResult` rows. What: An `insertedTradesAreReconciledAndPersisted` test in the ADV044 integration class autowires the three repository beans plus `ReconciliationService`, saves a matching trade pair, runs `runRecon(internalRepo.findAll(), externalRepo.findAll(), EXACT)`, then asserts on `reconResultRepo.findAll()`.
TICKET-ADV046 | ERROR | Types are missing need to revisit | JaCoCo coverage report ≥ 85% | Wire JaCoCo into the Maven build so that `mvn verify` produces a coverage report and fails the build when service-package coverage drops below 85%. What: The `jacoco-maven-plugin` (0.8.11) in `backend/pom.xml` declares three executions — `prepare-agent` (default), `report` (verify), and `check` (verify) — with a `<rules>` block targeting `com.dbtraining.reconx.service.*` and `com.dbtraining.reconx.repository.*` at `LINE` `COVEREDRATIO` `0.85`. | JaCoCo gate is wired in `backend/pom.xml` at 85% line coverage, but scoped only to `com.dbtraining.reconx.service.*` and `repository.*` — controllers, kafka consumers and config classes are outside the gate entirely.
TICKET-ADV047 |  |  | Refactor for edge cases | Add tests for three edge cases of `reconcile` and refactor the production code so all three pass. What: Three new `@Test` methods on `ReconciliationEngineTest` cover empty-internal (returns `Map.of()`), single-internal-no-external (one `BREAK` with reason `MISSING_EXTERNAL`), and all-mismatched (three `BREAK`s, `ReconSummary` reports `matched == 0`, `broken == 3`); the engine carries null/empty guards and a `(a, b) -> a` merge function in its `toMap` call.

## DAY_4
DAY 4 · 15 tickets · ADV048 – ADV062
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV048 | Already DONE | Not included in main | Create the multi-module Maven project | Stand up a five-module Maven reactor that builds end-to-end with `./mvnw -pl backend clean install`. What: A `backend/pom.xml` with `<packaging>pom</packaging>` and a `<modules>` list of `common`, `domain`, `repository`, `service`, `api`, plus a child `pom.xml` per module that declares only `<parent>` and its own `<artifactId>`. | The trainer copy is deliberately a single Maven module; the api/service/repository/domain split this ticket describes was never applied to `main`. Note a second module (`recon-audit-starter`, ADV095) was later added at the repo root but is NOT listed in the root POM's `<modules>`, so it is not part of the reactor build.
TICKET-ADV049 | Already DONE | Not included in main | Spring profiles: dev / uat / prod | Configure three Spring profiles so that the same JAR can boot against H2 in dev, Postgres in UAT, and a secrets-driven Postgres in prod. What: `application.yml` plus `application-dev.yml` (H2 in PostgreSQL mode), `application-uat.yml` (Postgres dialect), and `application-prod.yml` (Postgres dialect with `${DB_PASSWORD}` style env-var lookups and no literal credentials). | `application.yml` plus `application-{dev,uat,prod}.yml` all present. Worth knowing when reading the Kafka section: the `dev` profile overrides `missing-topics-fatal: false`, which is why a missing topic degrades quietly instead of failing startup.
TICKET-ADV050 | DONE | compiles | `@Entity Trade` with `@ManyToOne` + auditing | Define the `Trade` JPA entity with lazy-loaded relationships to `Counterparty` and `Instrument`, plus Spring Data auditing columns and Hibernate Envers tracking. What: `Trade.java` in the `domain` module annotated with `@Entity`, `@Table(name = "trades")`, `@EntityListeners(AuditingEntityListener.class)`, and `@Audited`, plus a `JpaConfig` class in `api` carrying `@EnableJpaAuditing`.
TICKET-ADV051 | DONE | compiles | `Instrument` entity with JSONB metadata | Map the `Instrument` entity, including a `Map<String, Object> metadata` field that stores as JSONB on Postgres and as a CLOB on H2. What: `Instrument.java` with a `Map<String, Object> metadata` field annotated `@Type(JsonBinaryType.class)` and `@Column(columnDefinition = "jsonb")`, backed by the `hypersistence-utils` dependency pinned in the parent POM.
TICKET-ADV052 | DONE |  | Hibernate Envers on the `Trade` entity | Verify that Envers writes one row per committed change to `Trade` into the `trades_aud` table, and expose two query methods on a `TradeHistoryService`. What: A `TradeHistoryService` in the `service` module with `revisionsFor(tradeId)` and `snapshotAt(tradeId, rev)` methods, both `@Transactional(readOnly = true)` and backed by Envers' `AuditReader`.
TICKET-ADV053 | Already DONE |  | DTO layer and `PagedResponse<T>` | Define `TradeRequest`, `TradeResponse`, and a generic `PagedResponse<T>` so controllers never leak JPA entities to the wire. What: Three Java `record` types — `TradeRequest` (validation-annotated input), `TradeResponse` (flat counterparty/instrument fields), and `PagedResponse<T>(items, page, size, totalElements, totalPages)` with a static `of(Page<E>, Function<E,T>)` factory.
TICKET-ADV054 | DONE |  | MapStruct mapper | Generate a Spring-managed `TradeMapper` bean that maps `Trade` to/from `TradeRequest`/`TradeResponse` at compile time. What: `TradeMapper.java` interface annotated `@Mapper(componentModel = "spring", unmappedTargetPolicy = ReportingPolicy.ERROR)` plus a `maven-compiler-plugin` block in `backend/api/pom.xml` declaring `mapstruct-processor` in `<annotationProcessorPaths>`.
TICKET-ADV055 | NOT DONE YET |  | `TradeRepository` with `@Query` | Define a Spring Data JPA repository that exposes a `findByTradeRef` derived query and a `findByFilters` JPQL query supporting optional date range, status, and counterparty filters. What: `TradeRepository extends JpaRepository<Trade, Long>, JpaSpecificationExecutor<Trade>` with a derived `findByTradeRef(String)` returning `Optional<Trade>` and a `@Query` JPQL `findByFilters(...)` using `(:param IS NULL OR ...)` for optional filters.
TICKET-ADV056 | DONE |  | Specification-based dynamic queries | Replace the `(:param IS NULL OR ...)` style with composable JPA Specifications so each filter is independently testable. What: `TradeSpecification` final class (private constructor) exposing four static `Specification<Trade>` factories: `tradeDateBetween`, `hasStatus`, `forCounterparty`, `refLike`, each returning `cb.conjunction()` when its argument is null/blank.
TICKET-ADV057 | Already DONE |  | Pagination on the list endpoint | Expose `GET /v1/trades` with optional filters and Spring's `Pageable` support, capped to a sane default page size. What: `TradeController` (a `@RestController` at `/v1/trades`) with a `GET` method that binds optional `from`/`to`/`status`/`counterpartyId` plus a `Pageable` annotated `@PageableDefault(size = 20, sort = "tradeDate", direction = Sort.Direction.DESC)`, returning `PagedResponse<TradeResponse>`.
TICKET-ADV058 | DONE | TESTED IN SWAGGER UI | Swagger / OpenAPI configuration | Configure springdoc-openapi so the running app exposes Swagger UI at `/api/swagger-ui.html` and groups endpoints into a `public` group and an `admin` group. What: `OpenApiConfig.java` declaring an `OpenAPI` bean (title, version, contact, `bearerAuth` HTTP/bearer/JWT security scheme) plus two `GroupedOpenApi` beans — `public` matching `/v1/trades/**` and `/v1/recon/**`, `admin` matching `/v1/admin/**` and `/actuator/**`.
TICKET-ADV059 | DONE |  | `DatabaseHealthIndicator` | Replace Boot's default DataSource health indicator with one that owns its own SQL, its own timeout, and its own details fields. What: A `@Component("reconxDatabase")` class extending `AbstractHealthIndicator`, executing `SELECT 1` against the injected `DataSource` with a 2-second query timeout and reporting `query`, `elapsedMs` details via try-with-resources.
TICKET-ADV060 | DONE |  | `KafkaHealthIndicator` | Add a conditional health indicator for the Kafka cluster that only registers when a `spring.kafka.bootstrap-servers` property is set. What: A `@Component("reconxKafka")` extending `AbstractHealthIndicator` and gated by `@ConditionalOnProperty(name = "spring.kafka.bootstrap-servers")`, building a Kafka `AdminClient` with 2s request and 3s default API timeouts and reporting `clusterId`, `nodeCount` via `describeCluster()`.
TICKET-ADV061 | DONE |  | Structured logging with MDC | Emit human-readable logs in `dev` and JSON logs in `uat`/`prod`, with a per-request `correlationId` (plus optional `tradeRef`) carried across the request via SLF4J's MDC. What: `backend/api/src/main/resources/logback-spring.xml` with two `<springProfile>` blocks (plain pattern for `dev`, `LogstashEncoder` JSON for `uat,prod`) plus a `@Component @Order(1) MdcFilter implements Filter` that puts `X-Correlation-Id` / `X-Trade-Ref` into MDC and clears it in `finally`.
TICKET-ADV062 | DONE |  | Global `@RestControllerAdvice` with RFC 7807 | Produce `application/problem+json` responses for every domain exception, validation failure, and uncaught error, using Spring's `ProblemDetail` API. What: A `@RestControllerAdvice` class `GlobalExceptionHandler` in the `api` module with `@ExceptionHandler` methods returning `ProblemDetail` for `TradeNotFoundException` (404), `DuplicateTradeRefException` (409), `ReconException` (422), `MethodArgumentNotValidException` (400), and a fall-through `Exception` handler (500).

## DAY_5
DAY 5 · 18 tickets · ADV063 – ADV080
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV063 | Already DONE |  | GET /api/v1/trades (paginated, filterable, sortable) | Expose a single GET endpoint that returns trades with optional filters and stable pagination metadata. What: `TradeController.list(...)` exposing `GET /api/v1/trades` that returns a `PagedResponse` envelope built from `Page<Trade>` via `JpaSpecificationExecutor` filters on `status`, `counterparty`, plus Spring Data `Pageable`.
TICKET-ADV064 | DONE | compiles & runs | POST /api/v1/trades (create + validation) | Create a new trade from a validated request body and return 201 with a `Location` header pointing to the new resource. What: `TradeController.create(...)` accepting `@Valid @RequestBody TradeRequest`, delegating to `TradeService.create(...)`, and returning `ResponseEntity.created(uri).body(response)` so the response carries HTTP 201 and a `Location: /api/v1/trades/{id}` header.
TICKET-ADV065 | DONE | compiles & runs & tested POSTs in console | PUT /api/v1/trades/{id} (full update) | Replace every mutable field of an existing trade in a single idempotent call. What: `TradeController.update(...)` mapped to `PUT /api/v1/trades/{id}` that reuses the validated `TradeRequest` from ADV064, copies every mutable field onto the loaded entity inside `@Transactional`, and throws `TradeNotFoundException` (mapped to 404) when the id is missing.
TICKET-ADV066 | CHECK | org.Hibernate.LazyInitializationException: Could not istantiate proxy….no session | PATCH /api/v1/trades/{id}/status | Update only the `status` field of a trade through a dedicated sub-resource. What: `TradeController.patchStatus(...)` mapped to `PATCH /api/v1/trades/{id}/status` accepting a `{ "status": "MATCHED" }` body with a JSR-380 validated enum, calling `TradeService.updateStatus(...)`, and returning the updated `TradeResponse`. | The team's recorded `LazyInitializationException` is resolved: `updateStatus` now loads through `tradeRepo.findByIdWithDetails(id)` (a fetch-join) rather than a plain `findById`, so the instrument/counterparty associations are initialised before the transaction closes. The same class of bug hit `GET /v1/trades` separately and was fixed upstream with a fetch-join Specification.
TICKET-ADV067 | DONE | compiles & runs & tested DELETE in console | DELETE /api/v1/trades/{id} (soft delete) | Logically delete a trade so it disappears from list responses while remaining in the database for audit. What: `TradeController.delete(...)` mapped to `DELETE /api/v1/trades/{id}` returning `ResponseEntity.noContent().build()`, plus a Liquibase changeset adding `deleted_at TIMESTAMP` to `trades` and a class-level `@SQLRestriction("deleted_at IS NULL")` on the `Trade` entity.
TICKET-ADV068 | DONE |  | POST /api/v1/recon/run | Trigger a reconciliation job asynchronously and return a job handle the client can poll. What: `ReconController.runRecon(...)` mapped to `POST /api/v1/recon/run` accepting a `@Valid ReconRunRequest`, generating a `UUID` jobId, and returning `ResponseEntity.accepted().body(Map.of("jobId", jobId, "status", "QUEUED"))` with a `Location` header pointing at the results endpoint. | Shipped as a stub: it returned a random `jobId` and `QUEUED` without ever invoking the reconciliation engine, with a comment implying an async worker that does not exist. A synchronous `engine.reconcile(...)` call was wired in later while doing ADV084, otherwise the ADV084 timer could never record a sample.
TICKET-ADV069 | DONE |  | GET /api/v1/recon/jobs/{jobId}/results | Return the paginated reconciliation breaks for a specific job. What: `ReconController.results(...)` mapped to `GET /api/v1/recon/jobs/{jobId}/results` taking `@PageableDefault(size = 50) Pageable`, querying `ReconBreakRepository`, and returning a `PagedResponse<ReconResultResponse>` reusing the ADV063 envelope. | The handler ignores its `jobId` path variable entirely and returns `breaks.findAll()` — results are not scoped to a job. This is currently load-bearing: the Recon Breaks page calls `/v1/recon/jobs/latest/results`, and the literal string `latest` is not a real job id — it only works because the parameter is discarded. Wiring `findByJobId` later will break that call site.
TICKET-ADV070 | DONE |  | PUT /api/v1/recon/results/{id}/resolve | Mark a single reconciliation break as resolved with a mandatory analyst note. What: `ReconController.resolve(...)` mapped to `PUT /api/v1/recon/results/{id}/resolve` accepting a `@NotBlank @Size(max = 500) note`, setting `status=RESOLVED`, `resolvedAt=now`, `resolutionNote=note` on the break inside `@Transactional`, and returning the updated `ReconResultResponse`.
TICKET-ADV071 | DONE |  | GET /api/v1/audit/trades/{tradeRef} | Expose Envers-backed revision history for a trade as a list of JSON snapshots. What: `AuditController` mapped to `/api/v1/audit` with `GET /trades/{tradeRef}` injecting `AuditLogRepository` (or Envers' `AuditReader`) and returning the revision list ordered oldest-first via `findByTradeRefOrderByEventTimestampAsc(...)`. | Endpoint returned an empty array: it read the Kafka-fed `audit_log` table, which nothing populated at the time (the producer and consumers were still Day-9 stubs). Rewired to Hibernate Envers via a new `AuditService` (+ `CustomRevisionEntity` / `CustomRevisionListener`, changeset 012). Verified: a freshly created trade now returns its revision with the correct `changedBy`. Note `CustomRevisionEntity` must NOT extend `DefaultRevisionEntity` — doing so changes generator resolution and fails with a missing `revinfo_seq`.
TICKET-ADV072 | DONE |  | JWT issuance on /api/auth/login | Authenticate a user with username/password and return a signed JWT containing the user's roles. What: `AuthController.login(...)` mapped to `POST /api/auth/login` plus a `JwtTokenProvider` that signs claims (`sub`, `role`, `iat`, `exp`) using `Keys.hmacShaKeyFor(secret)` where the secret comes from `${APP_JWT_SECRET:dev-default}` — never a hard-coded literal. | Wrong password returned HTTP 400, not 401 — `AuthController` threw `InvalidTradeException`, which is mapped to 400. Added a dedicated `InvalidCredentialsException` mapped to 401. Verified with curl. Separately: the guide's own login examples send `username`, but the DTO field is `email`.
TICKET-ADV073 | DONE |  | JwtAuthenticationFilter | Read the Bearer token off each request, validate it, and populate the Spring Security context. What: `JwtAuthenticationFilter extends OncePerRequestFilter` that pulls the `Authorization: Bearer ...` header, calls `JwtTokenProvider.parse(token)`, maps the `role` claim to a `SimpleGrantedAuthority("ROLE_" + role)`, and sets a `UsernamePasswordAuthenticationToken` on `SecurityContextHolder` — failing closed by clearing the context on `JwtException`.
TICKET-ADV074 | DONE |  | SecurityFilterChain + RBAC | Wire the filter into the chain and enforce URL-level RBAC for trades, recon, and audit endpoints. What: `SecurityConfig` exposing a `SecurityFilterChain` bean that disables CSRF, sets `SessionCreationPolicy.STATELESS`, permits `/api/auth/login` and `/actuator/health`, registers `JwtAuthenticationFilter` via `addFilterBefore(..., UsernamePasswordAuthenticationFilter.class)`, and binds `/api/v1/trades/**`, `/api/v1/recon/**`, `/api/v1/audit/**` to the role buckets seeded in ADV017.
TICKET-ADV075 | DONE |  | MockMvc: authenticated create returns 201 | Write a `@WebMvcTest` that posts a valid trade as a TRADER and asserts the 201 response with a `Location` header. What: `TradeControllerWebMvcTest` annotated `@WebMvcTest(TradeController.class)` with `@MockBean TradeService`, a `validRequest()` helper, and a `testCreateTrade_authenticated_returns201` method annotated `@WithMockUser(roles = "TRADER")` that POSTs with `.with(csrf())` and asserts 201 + `Location` + `jsonPath("$.id").value(42)`.
TICKET-ADV076 | DONE |  | MockMvc: unauthenticated returns 401 | Prove that a POST with no authentication is rejected before reaching the controller. What: `testCreateTrade_unauthenticated_returns401` method on the same `TradeControllerWebMvcTest` class, with no `@WithMockUser` and no `.with(csrf())`, asserting `status().isUnauthorized()`.
TICKET-ADV077 | DONE |  | MockMvc: VIEWER returns 403 | Prove that an authenticated user with the wrong role gets 403 on a state-changing endpoint. What: `testCreateTrade_viewerRole_returns403` method on `TradeControllerWebMvcTest` annotated `@WithMockUser(roles = "VIEWER")`, posting the same `validRequest()` with `.with(csrf())`, and asserting `status().isForbidden()` without stubbing the service.
TICKET-ADV078 | DONE |  | Full lifecycle integration test with Testcontainers | Drive a real Postgres-backed Spring Boot through the full trade lifecycle over HTTP. What: `TradeLifecycleIT` annotated `@SpringBootTest(webEnvironment = RANDOM_PORT) @Testcontainers` with a static `PostgreSQLContainer<>("postgres:16-alpine")` marked `@ServiceConnection`, using `TestRestTemplate` + ordered `@TestMethodOrder` tests that log in as `admin@db.com`, capture the JWT, then drive POST/GET/PATCH/recon-run/resolve over real HTTP.
TICKET-ADV079 | DONE |  | Verify Liquibase ran on a fresh DB | Prove that every Liquibase changeset applies cleanly against an empty Postgres and that seed data lands. What: `LiquibaseMigrationsIT` annotated `@Testcontainers @SpringBootTest @ActiveProfiles("test")` with its own `PostgreSQLContainer` and `@Autowired JdbcTemplate`, asserting `SELECT COUNT(*) FROM databasechangelog >= 13` and `SELECT COUNT(*) FROM trades WHERE deleted_at IS NULL >= 10`.
TICKET-ADV080 | DONE | compiles & runs & tested DELETE in console | API versioning + deprecation | Establish `/api/v1/...` as the contract prefix and demonstrate how to deprecate an endpoint cleanly. What: Every controller class carrying `@RequestMapping("/v1/...")` (combined with `server.servlet.context-path=/api` to yield `/api/v1/...`), plus one `@Deprecated(since = "v1.4.0", forRemoval = true)` example endpoint that sets `Deprecation: true`, `Sunset: <HTTP-date>`, and `Link: </api/v1/...>; rel="successor-version"` headers and returns `ResponseEntity.status(HttpStatus.GONE)`. | Versioning holds, but note the effective URL is `/api/v1/...` — the `/api` prefix comes from `server.servlet.context-path`, not from the controller mappings, which are declared as `/v1/...`.

## DAY_6
DAY 6 · 17 tickets · ADV081 – ADV097
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV081 | DONE | compiles & runs & cache hit recorded | `@Cacheable` on `InstrumentService.findBySymbol()` | Wrap the symbol lookup so a second call for the same symbol hits memory, not the database. What: `@Cacheable(value = "instruments", key = "#symbol")` on `InstrumentService.findBySymbol` plus a `CacheConfig` class carrying `@EnableCaching`. | `@Cacheable("instruments")` on `InstrumentService.findBySymbol`; cache hit confirmed via the Caffeine stats exposed by `recordStats()`.
TICKET-ADV082 | DONE | compiles & runs & cache hit recorded | Cache eviction: TTL 5 min instruments, 1 min counterparties | Configure two separately-named Caffeine caches with different time-to-live policies and turn on the stats hooks that Micrometer needs. What: A `CaffeineCacheManager` bean defining `instruments` (5 min TTL) and `counterparties` (1 min TTL) with `recordStats()` enabled so Micrometer can scrape hit/miss counts. | The per-cache TTLs are correct (instruments 5 min, counterparties 1 min) but they come from an explicit `SimpleCacheManager` bean in `CacheConfig.java` — NOT from the `spring.cache.caffeine.spec` block in `application.yml`. That YAML is dead config: declaring your own `CacheManager` bean switches off Boot's cache auto-configuration entirely. Editing the YAML to retune a TTL would appear to work and silently change nothing.
TICKET-ADV083 | DONE |  | Counter: `trade_created_total` | Emit a monotonically increasing counter every time a trade is successfully created. What: A `Counter.builder("trade_created_total").register(meterRegistry)` bean wired into `TradeService.createTrade`, incremented once per successful create. | Micrometer/Prometheus naming trap: a counter named `trade_created_total` is exposed as `trade_total` — the client treats `_created` as the reserved OpenMetrics creation-timestamp suffix and strips it when it directly precedes `_total`. Renamed to `trade_creation_total`. (Swapping to `micrometer-registry-prometheus-simpleclient` was tried first and broke `/actuator/prometheus` entirely — reverted.)
TICKET-ADV084 | Done | Dependency on a csv previously created for populating database | Timer: `reconciliation_duration_seconds` | Measure how long the reconciliation engine takes per batch and publish the distribution so server-side percentile queries work in PromQL. What: A `Timer` named `reconciliation_duration_seconds` registered with `publishPercentileHistogram(true)`, wrapping the recon engine call via `timer.record(() -> engine.run(batch))`. | Two real gaps. (1) `@Timed` was completely inert: no `TimedAspect` bean existed, and the actuator starter does NOT auto-configure one despite what the hint claims — needed `spring-boot-starter-aop` plus an explicit bean in `MetricsConfig`. (2) The engine was never called at all (see ADV068), so there was nothing to time. Also: rows inserted outside the API (raw seed SQL) can carry a `tradeRef` that fails domain validation, so the conversion must skip unconvertible rows or a single bad seed row fails the whole batch.
TICKET-ADV085 | Done |  | Gauge: `recon_break_count` | Publish a current-value sample of how many reconciliation breaks are currently OPEN. What: A `Gauge.builder("recon_break_count", breakRepository, r -> r.countByStatus(OPEN))` registered at startup so Micrometer pulls the live count on every scrape. | Verified already correct — no change needed.
TICKET-ADV086 | DONE |  | DistributionSummary: `trade_value_total` | Record the distribution of trade notional values (in USD) so you can answer questions like "what's the P95 trade size?" What: A `DistributionSummary.builder("trade_value_total").baseUnit("USD").publishPercentileHistogram(true)` recorded once per successful trade alongside the ADV083 counter. | `recordTradeValue()` was the only genuinely unimplemented part of the ADV083–086 block; implemented it and its call site in `TradeService.create`.
TICKET-ADV087 | DONE | Verified in Grafana (without data tho) | Grafana panel: API request rate by endpoint | A time-series panel showing requests-per-second broken out by URI. What: A Grafana time-series panel titled "API request rate by endpoint" running `sum by (uri) (rate(http_server_requests_seconds_count[1m]))` with the Y-axis unit set to req/s.
TICKET-ADV088 | DONE | Verified in Grafana (without data tho) | Grafana panel: API response time P50/P95/P99 | A three-line time-series panel showing median, 95th, and 99th percentile latency for each endpoint. What: A Grafana time-series panel with three queries — P50, P95, P99 — each shaped `histogram_quantile(<q>, sum by (le, uri) (rate(http_server_requests_seconds_bucket[5m])))` with the unit set to seconds.
TICKET-ADV089 | DONE | Verified in Grafana (without data tho) | Grafana panel: `trade_created_total` over time | A time-series panel showing trades-per-second created across the system. What: A Grafana time-series panel running `sum(rate(trade_created_total[1m]))` with the legend renamed to "trades/sec" and the unit set to req/s. | The dashboard panel for this metric was left querying `trade_created_total` after the ADV083 rename and silently showed no data; corrected to `trade_creation_total`.
TICKET-ADV090 | DONE | Verified in Grafana (without data tho) | Grafana histogram panel for `reconciliation_duration_seconds` | Visualise the distribution of recon engine latencies as a heatmap (density over time). What: A Grafana heatmap panel running `sum by (le) (rate(reconciliation_duration_seconds_bucket[1m]))` with the panel format set to Heatmap and the Y-axis labelled by bucket boundary.
TICKET-ADV091 | DONE | Verified in Grafana (without data tho) | Grafana stat panel: `recon_break_count` | A single big-number tile showing the current open-break count, coloured by severity. What: A Grafana stat panel bound to `recon_break_count` with thresholds green < 10, yellow 10-50, red > 50 and unit set to short.
TICKET-ADV092 | DONE | Verified via CURL (needs to be added to Prometheus still) | Grafana pie chart: trades by status | A pie chart showing the current breakdown of trades across statuses (PENDING, MATCHED, UNMATCHED, DISPUTED, CANCELLED). What: A Grafana pie chart fed by five `Gauge` registrations tagged `status=PENDING¦MATCHED¦UNMATCHED¦DISPUTED¦CANCELLED`, each pulling its count from `tradeRepository.countByStatus(...)`. | Gauge is registered by `TradesByStatusGauge` over the statuses PENDING / MATCHED / UNMATCHED / DISPUTED / CANCELLED.
TICKET-ADV093 | Already DONE |  | Alert: `recon_break_count > 50` for 5 min | A Prometheus alert rule that fires when there have been more than 50 open breaks continuously for 5 minutes. What: A Prometheus alert rule `HighOpenBreakCount` in `prometheus/rules/recon-alerts.yml` with `expr: recon_break_count > 50`, `for: 5m`, `labels: { severity: warning }`, and a `summary` annotation. | Rules live in `monitoring/prometheus/alerts.yml`; Prometheus reports all rules healthy once the stack is up.
TICKET-ADV094 | Already DONE |  | Alert: API P95 latency > 500ms for 3 min | A Prometheus alert rule on P95 HTTP latency exceeding 500 ms continuously for 3 minutes. What: A Prometheus alert rule `HighApiP95Latency` reusing the ADV088 query: `histogram_quantile(0.95, sum by (le) (rate(http_server_requests_seconds_bucket[5m]))) > 0.5`, `for: 3m`, with the current P95 value templated into the annotation.
TICKET-ADV095 | DONE | Build Success | Custom Spring Boot Starter: `recon-audit-starter` | Package an audit-event publisher as a reusable Spring Boot starter that auto-configures itself when added to a consumer's classpath. What: A separate Maven module `recon-audit-starter` containing `AuditAutoConfiguration` (gated by `@ConditionalOnProperty("reconx.audit.enabled", matchIfMissing=true)`) and a `META-INF/spring/org.springframework.boot.autoconfigure.AutoConfiguration.imports` file listing it. | The generated starter shipped a top-level `src/main/resources/application.properties` containing `spring.application.name=recon-aduit-starter` (typo included). A starter must never ship that file — it overrode the host application's own name and silently retagged EVERY Micrometer metric as `application="recon-aduit-starter"`, which breaks any Grafana query or alert keyed on `reconx`. File deleted. Also note the module is absent from the root POM's `<modules>`, so a fresh checkout needs a manual `cd recon-audit-starter && ./mvnw install` before the backend will resolve it, and it inherits a different Spring Boot parent (4.1.0) than the backend (3.5.0).
TICKET-ADV096 | DONE | Build Success & Verified in Console | JMX beans: toggle caching, adjust recon tolerance at runtime | Expose a `ReconConfig` MBean that lets an operator change the price tolerance and toggle caching at runtime from JConsole, plus invoke a `clearCache()` operation. What: A `@Component @ManagedResource(objectName = "reconx:type=ReconConfig")` bean exposing `priceTolerance` as a `@ManagedAttribute` (read/write, `volatile`) and `clearCache()` as a `@ManagedOperation`, with `spring.jmx.enabled=true` in `application.yml`. | MBean is reachable; `spring.jmx.enabled: true` is set in `application.yml`. `clearCache()` iterates `cacheManager.getCacheNames()`, so it clears both caches from ADV081/082.
TICKET-ADV097 | DONE | Verified in Console | Performance test: 100 concurrent requests | Drive 100 trade-creation requests at concurrency 10 against the running API and observe the load live on your Grafana panels. What: An `ab -n 100 -c 10 -H "Authorization: Bearer <jwt>" -p trade.json -T application/json http://localhost:8080/api/v1/trades` run (or k6 equivalent) with the throughput and P95 captured from both the tool output and Grafana.

## DAY_7
DAY 7 · 13 tickets · ADV098 – ADV110
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV098 | DONE | Need to test | Flexbox layout: sidebar, header, 3-col main, footer | Build the static-dashboard page shell using nested Flexbox containers — header on top, sidebar + main row in the middle, footer at the bottom, with a 3-card grid inside the main area. What: `static-dashboard/dashboard.html` plus `css/style.css` carrying a nested-Flexbox `.app-shell` (column) wrapping `.app-header`, `.app-body` (row containing `.app-sidebar` + `.app-main`), `.app-footer`, with `.dashboard-grid` wrapping three `.stat-card` children inside main. | Team note (original tracker): Check PR
TICKET-ADV099 | DONE | Need to test | CSS custom properties (design tokens) | Replace every hardcoded colour, spacing value, radius and shadow in your stylesheet with CSS custom properties defined on `:root`, so the next two exercises (theming and animations) can reference them. What: A `:root { }` block at the top of `static-dashboard/css/style.css` defining brand (`--color-primary`, `--color-gold`), surface (`--color-bg`, `--color-surface`, `--color-border`, `--color-text`), 4px-step spacing (`--space-1`…`--space-4`), and `--radius` tokens, with every component rule rewritten to read via `var(...)`.
TICKET-ADV100 | DONE | Need to test | Dark/light theme toggle | Add a toggle button that flips the whole dashboard between light and dark themes by mutating a single attribute on `<html>`, with the user's choice persisted across reloads and no flash of unstyled content. What: `static-dashboard/js/theme.js` carrying a head-loaded IIFE that reads `localStorage.getItem('reconx-theme')` and sets `data-theme` on `<html>` before paint, plus a `[data-theme="dark"]` block in `css/style.css` overriding the ADV099 surface tokens, wired to a `#theme-toggle` button click handler.
TICKET-ADV101 | DONE | Need to test | Real-time trade feed area with slide-in animation | Carve out a dedicated feed column in the dashboard that will host live trade cards, and style each `.trade-card` with an entrance animation that fires when the card is inserted. What: `<section id="trade-feed">` inside `.app-main` plus a `.trade-card` rule in `css/style.css` (using ADV099 tokens for padding/border/radius, with `.trade-card--matched` / `.trade-card--break` left-border modifiers) carrying `animation: slide-in 0.3s ease-out` against a `@keyframes slide-in` block.
TICKET-ADV102 | DONE | Need to test | CSS animations: fade-in, slide-in, pulse | Build out the animation library — three named keyframes (`slide-in`, `fade-in`, `pulse`) — and wire `pulse` to a danger-state alert. Honour `prefers-reduced-motion` so the animations disable for users who request it. What: Three `@keyframes` blocks (`slide-in`, `fade-in`, `pulse`) in `css/style.css`, a `.alert--danger` rule using `animation: pulse 2s ease-in-out infinite`, and a bottom-of-file `@media (prefers-reduced-motion: reduce)` block resetting `animation` / `transition` on `*, *::before, *::after`.
TICKET-ADV103 | DONE | Need to test | Responsive breakpoints: desktop, tablet, mobile | Make the shell survive three target widths — desktop (3-column cards, side-by-side sidebar + main), tablet (2-column cards, sidebar collapses to a top strip), mobile (1-column everything, smaller header). What: Two media queries at the bottom of `css/style.css` — `@media (max-width: 1024px)` narrowing the sidebar to ~180px and re-flowing `.dashboard-grid` to 2-across, and `@media (max-width: 640px)` collapsing to a single column with `display: none` (or top-strip) on `.layout__sidebar`.
TICKET-ADV104 | DONE | Need to test | Server-Sent Events subscription to `/api/v1/trades/stream` | Open a live subscription from the browser to the SSE endpoint scaffolded on Day 6 and update a visible "connection status" badge as the subscription opens, errors, and reconnects. What: `static-dashboard/js/sse.js` carrying an IIFE that constructs `new EventSource('/api/v1/trades/stream')` and wires `onopen` / `onmessage` / `onerror` handlers driving a `#sse-status` badge ("Live" / "Reconnecting…"), plus a `beforeunload` listener calling `sse?.close()`. | The backend half of this feed did not exist. No ticket in ANY day guide assigns building `GET /api/v1/trades/stream` — searching every README for `SseEmitter` returns zero hits — yet both this ticket and ADV116 are written purely as consumers of it. The endpoint plus a Kafka-driven broadcaster were added later to make the feed work end-to-end.
TICKET-ADV105 | DONE | Need to test | SSE handler with prepend-and-animate | Render each incoming SSE trade as a `.trade-card` at the **top** of the feed, replaying the TICKET-ADV101 slide-in animation on insert, and cap the feed at 50 entries so the DOM stays bounded. What: A `prependTradeRow(trade)` function inside `js/sse.js`'s IIFE that builds an `<article class="trade-card trade-card--<status> trade-card--new">` via `document.createElement`, uses `escapeHtml` + `Intl.NumberFormat` for safe field interpolation, calls `FEED_EL.prepend(row)`, and runs `while (FEED_EL.children.length > 50) FEED_EL.lastElementChild.remove()`.
TICKET-ADV106 | DONE | Need to test | Advanced data table (sortable, resizable, frozen header) | Build a trades table on `trades.html` with three behaviours — click-to-sort columns (with ascending/descending toggle), drag-to-resize columns from a handle, and a header row that stays visible while the body scrolls. What: `static-dashboard/trades.html` carrying a `.table-scroll` wrapper around `<table class="data-table" id="trades-table">` with `data-col` / `data-dir` / `data-type` / `.resize-handle` on each `<th>`, plus `js/trades.js` driving click-to-sort (`Array.prototype.sort` against a canonical `rows` array), drag-to-resize (`mousemove` / `mouseup` listeners on `document`, not the handle), and `position: sticky` on `thead th` for the frozen header.
TICKET-ADV107 | NOT EXIST |  | — ticket does not exist — | No such ticket exists in any guide — Day 7 ends at ADV106.
TICKET-ADV108 | NOT EXIST |  | — ticket does not exist — | No such ticket exists in any guide — Day 7 ends at ADV106.
TICKET-ADV109 | NOT EXIST |  | — ticket does not exist — | No such ticket exists in any guide — Day 7 ends at ADV106.
TICKET-ADV110 | NOT EXIST |  | — ticket does not exist — | No such ticket exists in any guide — Day 8 starts at ADV111.

## DAY_8
DAY 8 · 17 tickets · ADV111 – ADV127
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV111 | AlreadyDONE |  | Vite setup with path aliases | Configure the Vite project so `@/components/...` style imports resolve everywhere, with no `../../..` relatives in the tree. What: `frontend/vite.config.js` with a `resolve.alias` map (`@`, `@components`, `@hooks`, `@services`, `@context`, `@pages`) resolved via `fileURLToPath(new URL('./src/...', import.meta.url))`, plus `frontend/jsconfig.json` mirroring the same `paths` map. | Aliases and the dev-server proxy both live in `vite.config.js`; the proxy forwards `/api` to `localhost:8080`, which is what lets the SPA and backend run as separate processes in dev.
TICKET-ADV112 | DONE |  | HOC: `withAuth(Component)` | Build a higher-order component that wraps any page and redirects unauthenticated users to `/login` before the wrapped component ever renders. What: `frontend/src/components/withAuth.jsx` exporting a `withAuth(Component)` factory that reads `useAuth()`, returns `<Navigate to="/login" replace state={{ from: location.pathname }} />` when no user is present, and sets `WithAuth.displayName` for DevTools. | `authHeaders()` reads the `reconx-token` key from `sessionStorage` — tokens therefore do not survive a tab close, and they expire after 1 hour, which presents as sudden silent 401s that look like an auth regression but are not.
TICKET-ADV113 | DONE | Need to test | HOC: `withErrorBoundary(Component)` | Wrap any component in an ErrorBoundary that catches render errors and shows a recoverable fallback, exposed as an HOC so any page can opt in. What: `frontend/src/components/withErrorBoundary.jsx` containing a class `ErrorBoundary` with `getDerivedStateFromError` + `componentDidCatch` + a `Try again` reset, plus a `withErrorBoundary(Component)` factory composed outermost around `withAuth`.
TICKET-ADV114 | DONE | PASSED | Compound Component: `<DataTable>` | Build a `<DataTable>` whose `Header`, `Body`, and `Pagination` sub-components share sort state and pagination via internal context, so callers compose them as children rather than as flat props. What: `frontend/src/components/DataTable.jsx` exporting a root `<DataTable data>` that owns sort + page state via internal `DataTableContext`, with `DataTable.Header`, `DataTable.Body`, and `DataTable.Pagination` sub-components attached as static properties. | The page rendered an empty table regardless of database contents: the data-fetching `useEffect` was never written (left as a TODO) and `api.listTrades` was a stub that threw, swallowed by the page's own error handling — so it looked like 'no data' with nothing in the console or network tab pointing at the cause. Both implemented. Field names also had to be mapped at the fetch boundary: the REST DTO returns `instrumentSymbol`/`quantity`, but `TradeRow` expects `symbol`/`qty` (it was written against the SSE payload shape).
TICKET-ADV115 | DONE | PASSED | `useWebSocket(url, options)` | A custom hook that opens a WebSocket connection, exposes `{ data, status, send }`, and reconnects with exponential backoff on unexpected close. What: `frontend/src/hooks/useWebSocket.js` exposing `{ data, status, send }`, holding the socket + retry counter + reconnect timer in `useRef`s, and reconnecting on unexpected close with `min(maxDelay, baseDelay * 2 ** retries)` backoff. | Hook is implemented with exponential-backoff reconnect, but nothing imports it — no page or component uses `useWebSocket`. The live feed that actually ships uses SSE (ADV104/116), not WebSockets.
TICKET-ADV116 | DONE | PASSED | `useTradeStream()` with SSE | Subscribe to the existing Day 7 server-sent events endpoint and return `{ trades, isConnected }`, accumulating events into a bounded local buffer. What: `frontend/src/hooks/useTradeStream.js` opening an `EventSource` against `/stream/trades`, returning `{ trades, isConnected }`, and bounding the buffer to ~200 entries via an immutable `[next, ...prev].slice(0, 200)` updater. | The hook itself was fine; the badge read 'disconnected' purely because the backend endpoint it targets did not exist (see ADV104). Also worth recording for demos: the dashboard is live-only by design — there is no history replay, so it stays at zero until a trade is created while the tab is open.
TICKET-ADV117 | DONE | PASSED | `useDebouncedSearch(query, delay)` | A hook that takes a raw query string and a delay, and returns a debounced version that only updates once typing has paused for `delay` ms. What: `frontend/src/hooks/useDebouncedSearch.js` with one `useState` + one `useEffect([query, delay])` whose cleanup calls `clearTimeout` so only the trailing keystroke survives the debounce window.
TICKET-ADV118 | DONE | PASSED | `useInfiniteScroll(loadMore)` | A hook that returns a `sentinelRef`; attaching it to a sentinel element at the bottom of a list calls `loadMore()` whenever that sentinel scrolls into view. What: `frontend/src/hooks/useInfiniteScroll.js` returning a `sentinelRef`; an `IntersectionObserver` created once observes the sentinel, and a `useRef` mirrors the latest `loadMore` so the callback dodges stale closures without recreating the observer. | Implemented, but unused — no page imports `useInfiniteScroll`. The Trades page paginates with explicit prev/next buttons instead.
TICKET-ADV119 | DONE | PASSED | `React.memo` on `<TradeRow />` | Wrap the trade row component in `React.memo` with a custom equality check so that rows only re-render when fields they actually display change. What: `frontend/src/components/TradeRow.jsx` exporting `React.memo(TradeRowImpl, areEqual)` where `areEqual` compares only the rendered fields (`id`, `status`, `price`) plus `prev.onClick === next.onClick`. | `api.updateStatus` and `api.deleteTrade` were stubs that threw; implemented and verified against the live backend (200 and 204). No UI control calls them yet.
TICKET-ADV120 | DONE | PASSED | `useMemo` for portfolio value and P&L | Wrap genuinely expensive aggregations (portfolio value, matched/unmatched/disputed counts and totals) in `useMemo` so they recompute only when the trades array actually changes. What: `useMemo`-wrapped portfolio value, P&L, and matched/unmatched/disputed counts inside `Dashboard.jsx`, each with `[trades]` as the sole dep so unrelated state flips skip the reduce.
TICKET-ADV121 | DONE | PASSED | `useCallback` on event handlers passed to memoised children | Wrap handlers passed into `<TradeRow />` (and similar memo children) with `useCallback` so the memoisation from TICKET-ADV119 actually holds. What: `const handleSelect = useCallback((id) => setSelectedId(id), [])` in `Trades.jsx` (and equivalents elsewhere), passed as the `onClick` prop on `<TradeRow />` instead of an inline arrow. | `api.runRecon`, `api.reconResults` and `api.audit` were stubs that threw; implemented and verified (202 with a real jobId, 200, 200). Audit/Recon/DLQ pages have since been added and now call `audit`, `listAuditEvents`, `listReconBreaks`, `resolveReconBreak`, `listDlq` and `replayDlq`. Still unused by any page: `runRecon` and `reconResults` — nothing in the SPA triggers a reconciliation run or reads a specific job's results.
TICKET-ADV122 | DONE | PASSED | `React.lazy` + `Suspense` for route-based code splitting | Lazily import each page component and put one `<Suspense>` boundary at the right level of the layout so first navigation downloads a per-page chunk and re-navigation hits the cache. What: `const Dashboard = lazy(() => import('@pages/Dashboard'))` (one per page) wrapped in a single `<Suspense fallback={<PageSkeleton />}>` placed inside the layout so the nav/header survive navigation.
TICKET-ADV123 | DONE | PASSED | Trade entry form: RHF + Yup | Build the `/trades/new` page as a `react-hook-form` form validated against a `yup` schema that covers trade ref, instrument, quantity, price, and trade date. What: `frontend/src/pages/AddTrade.jsx` using `useForm({ resolver: yupResolver(schema), mode: 'onBlur' })` with a Yup schema covering `tradeRef` (regex `^[A-Z]{3}-\d{8}-\d{4}$`), `quantity`/`price` (`yup.number().positive()`), and `tradeDate`. | Submitting the form failed outright with 'TICKET-ADV123 not implemented' — `api.createTrade` was a stub. Implemented it, and normalised `tradeDate`: yup's `date()` schema casts the input to a JS `Date`, but the backend expects a plain `yyyy-MM-dd` string, so this would have failed immediately after.
TICKET-ADV124 | DONE | PASSED | Theme context (light/dark) | Provide a `ThemeProvider` that exposes a `useTheme()` hook, persists the choice to `localStorage`, respects `prefers-color-scheme` on first visit, and flips `data-theme` on `<html>` so the existing CSS takes over. What: `frontend/src/context/ThemeContext.jsx` exposing `<ThemeProvider>` + `useTheme()`, seeded from `localStorage.theme` then `prefers-color-scheme`, with a `useEffect` that flips `document.documentElement.dataset.theme`.
TICKET-ADV125 | DONE | PASSED | RTL test: dashboard summary cards | Render `<Dashboard />` with seeded trade data inside the required providers and assert each summary card is present. What: `frontend/src/pages/Dashboard.test.jsx` with a `renderWithProviders(ui)` helper wrapping `ui` in `AuthContext.Provider` -> `ThemeProvider` -> `MemoryRouter`, and one synchronous `it('shows summary cards', ...)` asserting three `getByRole('heading', { name: /.../i })` + one regex value check.
TICKET-ADV126 | NOT EXIST |  | — ticket does not exist — | No such ticket exists in the Day 8 guide — numbering gap.
TICKET-ADV127 |  |  | Profile with React DevTools, fix unnecessary re-renders *(fast-finisher)* | Open the React DevTools Profiler, record a session that exposes excessive re-renders on the dashboard, identify the specific culprit, and apply a fix that reduces the render count in a follow-up recording. What: A *before* Profiler trace showing the excess renders, a fix (typically hoisting an inline arrow into `useCallback` or memoising a context provider's value with `useMemo`), and an *after* trace with the same interactions and materially fewer renders for the named culprit.

## DAY_9
DAY 9 · 18 tickets · ADV128 – ADV145
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV128 | DONE | Verified in Kafdrop | Kafka topics (trade-events, recon-results, system-alerts) | Declare the three primary Kafka topics plus the trade-events DLQ topic so the broker creates them automatically on application startup. What: A `KafkaTopicsConfig.java` `@Configuration` class declaring four `NewTopic` beans: `trade-events` (3P), `trade-events-dlq` (3P), `recon-results` (2P), `system-alerts` (1P), each with replication factor 1, plus `public static final String` constants for every topic name. | The `@Profile("!dev & !test")` guard had been commented out, so the `NewTopic` beans ran in dev too. With no local broker, `KafkaAdmin` blocked startup retrying `localhost:9092`: measured 48.9 s to boot versus 8.9 s once the annotation was restored. Consequence worth knowing: topics are deliberately NOT auto-created in dev, so create them manually with the right partition counts — the broker's own auto-create will otherwise make them single-partition the first time a consumer subscribes, which silently defeats the partitioning this ticket sets up.
TICKET-ADV129 | DONE |  | TradeEventProducer | Build a producer component that publishes `TradeEvent` messages to the `trade-events` topic, keyed by `tradeRef` so all events for the same trade preserve order on one partition. What: A `TradeEventProducer` `@Component` exposing `publish(TradeEvent event)` that sends to `trade-events` keyed by `event.tradeRef()` and logs failures via `whenComplete` instead of `.get()`. | Producer code was correct, but nothing ever called `publish()`: `TradeService.create` and `update` had no call at all, and `updateStatus` and `softDelete` had theirs commented out — so the entire downstream pipeline was dead end-to-end while every individual ticket looked complete. Fixed by a teammate (commit 50cb1ea).
TICKET-ADV130 | Already DONE |  | TradeEvent payload | Define the immutable Kafka event payload as a Java record carrying both event metadata and a before/after trade snapshot. What: An immutable `TradeEvent` Java `record` in the `dto` package with `eventId`, `tradeRef`, `eventType`, `timestamp`, `before`, `after`, a nested `EventType` enum (`TRADE_CREATED`, `TRADE_UPDATED`, `TRADE_CANCELLED`), and three static factories `created` / `updated` / `cancelled`.
TICKET-ADV131 | DONE | Reconciliation Engine not fully implemented!!!!!!!!!! Solution not given | ReconciliationConsumer | Wire a consumer on the `trade-events` topic that triggers reconciliation logic for every event, in the `recon-service` consumer group. What: A `ReconciliationConsumer` `@Component` with `@KafkaListener(topics = "trade-events", groupId = "recon-service")` dispatching on `eventType` to `reconEngine.scheduleRecon(tradeRef)` for `TRADE_CREATED` / `TRADE_UPDATED` and `cancelPendingRecon(tradeRef)` for `TRADE_CANCELLED`.
TICKET-ADV132 | DONE | Producer sents event, consumer receives via kafka in logs. Messages seen in Kafdrop | AuditEventConsumer | Persist every `TradeEvent` to the `audit_log` table (built on Day 1) using a separate consumer group, so the event log becomes the foundation of the event-sourcing rebuild in TICKET-ADV137. What: An `AuditEventConsumer` `@Component` with `@KafkaListener(topics = "trade-events", groupId = "audit-service")`, annotated `@Transactional`, that builds an `AuditLogEntry` from each `TradeEvent` (operation = `eventType.name()`, before/after snapshots, `occurredAt = event.timestamp()`) and saves via `AuditLogRepository`. | Works, and is the piece that finally populates `audit_log` — which is what makes ADV137 and ADV138 return real data rather than an empty list.
TICKET-ADV133 | DONE |  | AlertConsumer | Listen on the `system-alerts` topic and surface every alert at WARN level, with an optional pluggable sink for Slack or another notifier. What: An `AlertConsumer` `@Component` listening on `system-alerts` (groupId `alert-service`) that logs each `SystemAlert` at WARN with severity / code / message and forwards to a constructor-injected `AlertSink` (default `NoopAlertSink`). | Latent and still unfixed: `application.yml` sets `spring.json.value.default.type=TradeEvent` globally with `use.type.headers=false`, so the default container factory forces EVERY topic — including `system-alerts`, which this listener expects as a plain `String` — to deserialize as `TradeEvent`. A genuine string alert would fail deserialization. Needs a dedicated String-typed container factory for this one listener.
TICKET-ADV134 | DONE |  | Dead-Letter Queue wiring | Configure a `DefaultErrorHandler` that publishes records to a `*-dlq` topic on the same partition number after retries are exhausted. What: A `KafkaErrorHandlerConfig.java` `@Configuration` declaring a `DefaultErrorHandler` backed by a `DeadLetterPublishingRecoverer` whose destination resolver maps each failed record to `new TopicPartition(record.topic() + "-dlq", record.partition())`, wired into the trade-events container factory, with deserialization exceptions added to the not-retryable list. | Verified live against a real broker: a genuine consumer failure retried and then landed on `trade-events-dlq` on the SAME partition number, which the destination resolver guarantees by construction. Note that no `tradeEventListenerContainerFactory` bean exists even though the reference solution wires into one by that name — an unqualified `DefaultErrorHandler` bean is picked up by Boot's autoconfigured factory instead, which is enough.
TICKET-ADV135 | DONE |  | Retry strategy with exponential backoff | Tune the error handler's backoff so retries follow an exponential schedule (roughly 1s, 2s, 4s) and stop after about three attempts before the message lands in the DLQ. What: An `ExponentialBackOff` (initial 1000 ms, multiplier 2.0, `setMaxElapsedTime` ~8 s) wired into the `DefaultErrorHandler` so retries fire at ~1 s / 2 s / 4 s and then the recoverer publishes to DLQ. | Retry timeline confirmed from timestamps in the live log: attempts at ~1 s, ~2 s and ~4 s, then the DLQ publish.
TICKET-ADV136 | DONE |  | DLQ consumer and replay endpoint | Build a consumer on `trade-events-dlq` that records each failed message, plus an admin REST endpoint that re-publishes a single DLQ message back to the main topic. What: A `DlqConsumer` `@Component` on `trade-events-dlq` (groupId `dlq-monitor`) that persists a `DlqMessage` row per failure (with `eventId`, `originalTopic`, `partition`, `offset`, `payload`, `reason`, `firstSeen`), plus a `POST /api/v1/admin/dlq/replay` endpoint (query params `eventId` required, `dryRun` default false) protected by `@PreAuthorize("hasRole('ADMIN')")` that re-publishes via `TradeEventProducer` and deletes the DLQ row. | Two deviations from the guide were required. (1) The failure reason arrives in `KafkaHeaders.DLT_EXCEPTION_MESSAGE`, not `EXCEPTION_MESSAGE` as the hint states — using the latter silently stores `null`. (2) `@PreAuthorize` is inert in this codebase because `@EnableMethodSecurity` is never enabled anywhere, so ADMIN-only enforcement was added as a `SecurityConfig` path matcher instead. Dry-run, real replay and row deletion all verified; a replayed message correctly re-enters the same retry→DLQ cycle.
TICKET-ADV137 | DONE |  | Event sourcing rebuild | Build a `TradeAggregator` service whose `rebuild(String tradeRef)` method reads every event for that trade from `audit_log`, ordered by timestamp, and folds them into the current state. What: A `TradeAggregator` `@Service` with `Optional<JsonNode> rebuild(String tradeRef)` that reads `auditRepo.findByTradeRefOrderByOccurredAtAsc(tradeRef)` and folds events into running state (`TRADE_CREATED` / `TRADE_UPDATED` set state to `afterData`; `TRADE_CANCELLED` sets it to null), returning `Optional.empty()` when no events exist. | The guide assumes `JsonNode` snapshots, but this codebase stores `before`/`after` as plain `String` (and the getters are `getBeforeState` / `getAfterState`, not `getAfterData`), so `rebuild` returns `Optional<String>`. Verified the full fold: CREATED→PENDING, UPDATED→SETTLED, CANCELLED→empty.
TICKET-ADV138 | Already DONE | Added SSE endpoint for frontend | Admin audit endpoint | Expose `GET /api/v1/audit/trades/{tradeRef}/events` so admins and recon analysts can fetch the full event history for any trade, oldest first. What: A `@RestController` at `/api/v1/audit/trades` with `@GetMapping("/{tradeRef}/events")` returning `List<TradeEvent>` ordered by timestamp ascending, protected by `@PreAuthorize("hasAnyRole('ADMIN','RECON_ANALYST')")`. | Endpoint already existed and was already role-gated correctly; it simply returned `[]` until ADV132's consumer began populating `audit_log`. The ADV137 rebuild was exposed alongside it.
TICKET-ADV139 | DONE |  | Kafka metrics via Micrometer | Expose Kafka client metrics on the Prometheus actuator endpoint so Grafana can scrape them. What: `application.yml` with `management.metrics.binders.kafka.enabled: true`, `spring.kafka.consumer.properties.metric.reporters: io.micrometer.core.instrument.binder.kafka.KafkaClientMetrics`, and `prometheus` added to `management.endpoints.web.exposure.include`. | The guide's own reference config is wrong and actively breaks the app: setting `spring.kafka.consumer.properties.metric.reporters` to `io.micrometer...KafkaClientMetrics` crashes consumer construction with an NPE, because that class is a Micrometer binder for an already-built client, not a Kafka `MetricsReporter` to be instantiated reflectively. The working fix is `management.metrics.binders.kafka.enabled: true` on its own — Boot's `KafkaMetricsAutoConfiguration` does the rest.
TICKET-ADV140 | DONE |  | Grafana panel: consumer lag by topic | Add a Time Series panel to Grafana that shows consumer lag aggregated per topic, with red/yellow thresholds. What: A Grafana Time Series panel titled "Consumer lag by topic" in the Kafka dashboard row with query `sum by (topic) (kafka_consumer_records_lag)` and thresholds yellow at 100, red at 1000. | The real metric name on this client (Kafka 3.9.1) is `kafka_consumer_fetch_manager_records_lag` — note the `fetch_manager` infix the ticket text omits. The bare `kafka_consumer_records_lag` does not exist and the panel would render 'No data'. Labels available for grouping are `topic`, `partition` and `client_id`.
TICKET-ADV141 | DONE |  | Grafana panel: messages/sec produced vs consumed | Add a Time Series panel that overlays produce rate and consume rate so you can spot a slow consumer at a glance. What: A Grafana Time Series panel titled "Throughput: produced vs consumed" overlaying `sum(rate(kafka_producer_record_send_total[1m]))` and `sum(rate(kafka_consumer_records_consumed_total[1m]))` as series labelled `produced` and `consumed`. | Same `fetch_manager` infix applies to `kafka_consumer_fetch_manager_records_consumed_total`. `kafka_producer_record_send_total` is correct exactly as written.
TICKET-ADV142 | DONE |  | Grafana panel: DLQ count and alert | Add a Stat panel showing total messages routed to the trade-events DLQ, plus an alerting rule that fires on any DLQ activity. What: A Grafana Stat panel titled "DLQ message count" with query `sum(kafka_consumer_records_consumed_total{topic="trade-events-dlq"})` plus a `KafkaDlqMessages` alerting rule (severity `critical`, fires when expression > 0 for one minute, annotation pointing operators to `/api/v1/admin/dlq`). | Panel and `KafkaDlqMessages` rule added; Prometheus reports the rule healthy. Alerting on the consumed *count* rather than lag is the right call here — a fast DLQ consumer keeps lag at zero even though a message genuinely landed in the DLQ and needs a human.
TICKET-ADV143 | DONE |  | Integration test: end-to-end happy path | Write a `@SpringBootTest` that boots Testcontainers Kafka, publishes 100 events, and waits until 100 audit rows are persisted — using Awaitility instead of `Thread.sleep`. What: A `KafkaPipelineIT` `@SpringBootTest` + `@Testcontainers` class under `backend/src/test/java/com/dbtraining/reconx/kafka/` with a static `KafkaContainer` (`confluentinc/cp-kafka:7.6.0`), a `@DynamicPropertySource` for `spring.kafka.bootstrap-servers`, and an Awaitility assertion that publishes 100 `TradeEvent.created(...)` and waits for `auditRepo.count()` to increase by 100 within 30 s. | Passes consistently. Had to diverge from the reference: no `TradeEvent.created(...)` static factories exist in this codebase, so the record is constructed directly. Awaitility had to be added to the POM. Note there is no `maven-failsafe-plugin` configured, so `*IT` classes never run under a plain `mvn verify` — they only execute via an explicit `-Dtest=ClassName`, which is exactly how the guide's verify commands invoke them.
TICKET-ADV144 | DONE |  | Integration test: DLQ on consumer failure | Write a Testcontainers test that proves a failing listener causes the message to land on `trade-events-dlq` after retries are exhausted. What: A `DlqRoutingIT` Testcontainers test that uses `@MockBean ReconciliationEngine` with `doThrow(new RuntimeException("boom"))`, publishes one `TradeEvent.created(...)` for `tradeRef = "TRD-DLQ-1"`, and asserts via Awaitility that a throwaway raw consumer (with `JsonDeserializer.TRUSTED_PACKAGES = "*"`) on `trade-events-dlq` sees that tradeRef within 30 s. | Two fixes were needed over the reference code. (1) The raw assertion consumer must set `JsonDeserializer.VALUE_DEFAULT_TYPE` — the producer sends no type headers, so without it the test dies with `RecordDeserializationException`. (2) The real signature is `scheduleRecon(TradeEvent)`, not `scheduleRecon(String)` as the guide's mock assumes.
TICKET-ADV145 | DONE |  | AI-assisted Kafka consumer config review | Use Claude to review your Kafka consumer configuration for production readiness, then file a PR that records each finding with an explicit accept/reject/defer decision. What: A PR description listing every finding Claude returned on the Kafka consumer config review (covering backpressure / poll tuning, error handling and retry / DLQ, idempotence, observability, security) with config key, recommended value, one-line justification, plus a team decision column (accept / reject / defer) with at least one of each and a rationale per row. | Review run against the live config. Decisions: ACCEPT explicit `acks: all` and `enable.idempotence: true` (already Kafka 3.x's effective default, so zero behavioural risk, but it pins the guarantee against a future client default change); REJECT SASL_SSL for now (no secured broker exists in this environment, so enabling it would break connectivity rather than improve anything); DEFER listener `concurrency`, backoff jitter, and correlation-ID propagation across the Kafka boundary (all performance/observability polish rather than functional gaps). Full table in `docs/reviews/TICKET-ADV145-decisions.md`.

## DAY_10
DAY 10 · 20 tickets · ADV146 – ADV165
Ticket | Status | Test | Title | Description (What & how it was achieved) | Observation
TICKET-ADV146 | Already DONE | Does not run independently | Backend multi-stage Dockerfile | Containerise the Spring Boot backend with a small, secure runtime image. What: `backend/Dockerfile` with two stages — `eclipse-temurin:25-jdk` build stage and `eclipse-temurin:25-jre-alpine` runtime stage running as a non-root `reconx` user — plus a sibling `backend/.dockerignore`.
TICKET-ADV147 | Already DONE | Does not run independently | Frontend multi-stage Dockerfile and nginx.conf | Build the Vite SPA in node-alpine and serve the static `dist/` from nginx-alpine. What: `frontend/Dockerfile` (node-alpine build stage running `npm ci && npm run build`, nginx-alpine runtime stage) plus `frontend/nginx.conf` with a SPA fallback and an `/api/` proxy_pass to the `backend` service.
TICKET-ADV148 | DONE | All containers start | docker-compose.yml with 7 services | Compose the full stack (postgres, zookeeper, kafka, backend, frontend, prometheus, grafana) so one command boots it all. What: `docker-compose.yml` defining seven services (`postgres`, `zookeeper`, `kafka`, `backend`, `frontend`, `prometheus`, `grafana`) on one bridge network, with `depends_on: service_healthy` gating the `backend` on Postgres and Kafka. | Verified bringing the stack up service-by-service (zookeeper, kafka, kafdrop, prometheus, grafana) rather than all at once, which is the practical way to work alongside a locally-run backend.
TICKET-ADV149 | Already DONE | Target shows State "UP" | Prometheus scrape config | Configure Prometheus to scrape the Spring Boot actuator metrics endpoint and Kafka JMX. What: `monitoring/prometheus/prometheus.yml` with `scrape_configs` jobs for `backend` (path `/actuator/prometheus`, target `backend:8080`) and `kafka` JMX, mounted read-only into the prometheus container at `/etc/prometheus/prometheus.yml`. | `monitoring/prometheus/prometheus.yml` scrapes the target `backend:8080`, i.e. the compose service name. That means Prometheus only sees metrics from the containerised backend — a backend started locally via `./mvnw spring-boot:run` is not scraped, and the panels stay empty even though `/actuator/prometheus` is serving data correctly.
TICKET-ADV150 | Already DONE | Confirmed | Grafana provisioning (datasource + dashboards) | Auto-provision the Prometheus datasource and the ReconX dashboard so Grafana is usable on first boot. What: `monitoring/grafana/provisioning/datasources/prometheus.yml` plus `monitoring/grafana/provisioning/dashboards/reconx.yml` and a JSON dashboard under `monitoring/grafana/dashboards/`, mounted into the grafana container so the ReconX folder appears with no manual import. | Grafana provisioning is picked up from `monitoring/grafana/provisioning/`; the dashboard loads with its panels intact and the `reconx-prometheus` datasource UID resolves.
TICKET-ADV151 | Already DONE | Liquibase and postgres confirmed | Liquibase migrations on container startup | Ensure Liquibase changesets apply automatically when the stack boots, before the backend accepts traffic. What: `backend/src/main/resources/application-docker.yml` with `spring.liquibase.enabled: true`, `change-log:` pointed at the ADV012 master changelog, and `spring.jpa.hibernate.ddl-auto: validate` pinned for the docker profile.
TICKET-ADV152 | Only verification | All containers up and running | Verify every healthcheck works in isolation | Confirm each container's healthcheck transitions from `starting` to `healthy` within its retry budget. What: Per-service `healthcheck:` blocks in `docker-compose.yml` for postgres (`pg_isready`), kafka (`kafka-topics --list`), backend (`wget /actuator/health`), with `interval`, `timeout`, `retries`, and `start_period` tuned per service.
TICKET-ADV153 |  | Smoke Test | Compose smoke-test script | Write a single shell script that brings the stack up and proves end-to-end correctness in seven steps. What: `scripts/smoke-test.sh` running `set -euo pipefail` and exercising seven steps: stack up, login, trade POST, Kafka event consumed, Postgres audit row, Prometheus target UP, Grafana datasource reachable. | `scripts/smoke-test.sh` exists. Be aware it opens with `docker compose down -v`, so running it destroys any stack you currently have up along with its volumes (including the Postgres data volume).
TICKET-ADV154 | Don't do? | GitHub Actions????????????????? | CI workflow with GHCR push | Write a GitHub Actions workflow that lints, tests, builds, and pushes Docker images to GHCR on every push to main. What: `.github/workflows/ci.yml` with `lint`, `test`, `build-and-push` jobs chained via `needs:`, top-level `permissions: packages: write`, and `docker/build-push-action` pushing `ghcr.io/<org>/reconx-{backend,frontend}` tagged `:latest` and the commit SHA.
TICKET-ADV155 | Don't do? | GitHub Actions????????????????? | Liquibase validate step in CI | Catch migration mistakes (pending changesets, checksum mismatches, XML parse errors) before any test runs. What: A `Liquibase validate` step inside the `test` job in `.github/workflows/ci.yml`, running `./mvnw -B liquibase:validate` against the Postgres service container immediately after `setup-java`.
TICKET-ADV156 | Don't do? | GitHub Actions????????????????? | JaCoCo coverage gate at 85% | Fail the CI build if line coverage drops below 85% or branch coverage drops below 70%. What: `org.jacoco:jacoco-maven-plugin` in `backend/pom.xml` with `prepare-agent`, `report`, and a `coverage-gate` `check` execution bound to `verify`, plus the matching `Coverage gate` step in `.github/workflows/ci.yml` enforcing >=85% line and >=70% branch.
TICKET-ADV157 | Don't do? | GitHub Actions????????????????? | Static analysis (Checkstyle) | Add Checkstyle to the backend build so style and structural rules are enforced in CI. What: `maven-checkstyle-plugin` in `backend/pom.xml` with `<failOnViolation>true</failOnViolation>` bound to the `validate` phase, plus `backend/checkstyle.xml` (Google checks minus the noisiest rules) and explicit `<suppress>` entries justifying anything turned off.
TICKET-ADV158 |  | Loadtest | k6 load test (200 concurrent trade creations) | Run a 2-minute load test with 200 virtual users posting trades, asserting p95 latency under 800 ms and error rate under 2%. What: `loadtest/trade-creation.js` using the `constant-vus` executor (200 VUs, 2 min), a `setup()` that logs in once and returns the JWT, and `thresholds` for `http_req_failed`, custom `trade_post_latency_ms` (p95<800, p99<2000), and `trade_post_errors` (rate<0.02).
TICKET-ADV159 |  | Loadtest | Grafana screenshots (baseline, under load, recovery) | Capture three rendered Grafana panels — steady state, under load, and recovery — for the README and demo deck. What: Three rendered PNGs at `docs/screenshots/grafana-baseline.png`, `grafana-under-load.png`, and `grafana-recovery.png` captured via Grafana's "Direct link rendered image" share option, not OS screenshots.
TICKET-ADV160 |  | Mermaid | Mermaid architecture diagrams | Produce two Mermaid diagrams in the README — runtime architecture and CI/CD flow. What: Two fenced ` ```mermaid` blocks in the README: a top-down runtime graph (User → Frontend → Backend → Postgres, Backend → Kafka → listeners, Backend → Prometheus → Grafana) and a left-to-right CI/CD graph (Developer → GitHub → Actions lint→test→coverage→docker → GHCR → Demo Laptop).
TICKET-ADV161 | Already DONE? | Readme | Comprehensive top-level README | Write a README that a recruiter can read in 60 seconds on a phone and a new joiner can use to bring the stack up in three commands. What: A top-level `README.md` with above-the-fold elevator pitch + three-command Quick Start, a 10-section TOC (Architecture, Tech stack, API docs, Monitoring, Kafka topics, Load test results, CI/CD, Deploy runbook, Default creds, Troubleshooting), and inlined ADV160 Mermaid diagrams plus ADV159 Grafana screenshots.
TICKET-ADV162 | DONE | Presentation | Demo deck (10 slides) | Produce a 10-slide deck that anchors the 20-minute demo without becoming a teleprompter. What: `docs/demo-deck.pdf` (or `.pptx`) with exactly 10 slides — title, problem, architecture (ADV160 Mermaid), tech stack by layer, live demo intro, Kafka/recon, CI/CD, monitoring (ADV159 screenshots), learnings, Q&A — each slide capped at three bullets.
TICKET-ADV163 | DONE | Rehearsal | Rehearsal (20-minute runsheet, run twice) | Produce a minute-by-minute runsheet and execute two full rehearsals before the live slot. What: `docs/demo-runsheet.md` with minute-by-minute timing (3 min context, 8 min live demo, 5 min code walkthrough, 4 min Q&A) and timestamped screen switches — login → trade POST → Kafdrop → Grafana → audit row.
TICKET-ADV164 |  | Release | Tag release v1.0.0 | Cut and push an annotated `v1.0.0` tag from a green main, verifying CI rebuilds and tags the GHCR images. What: An annotated `v1.0.0` tag created with `git tag -a v1.0.0 -m "Release v1.0.0 — ..."` from a green `main`, pushed via `git push origin v1.0.0`, picked up by the ADV154 workflow's `on.push.tags: ['v*']` trigger.
TICKET-ADV165 |  | Retro | Retrospective | Each team fills in a structured retrospective in `docs/retrospective.md` and links it from the README. What: `docs/retrospective.md` with five sections (What worked, What didn't, What would you change, What surprised you, Technical notes for the next cohort) plus a team roster naming each member's primary role, linked from the ADV161 README's Team section.